## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed) | Cross-Team Acceptance Test | Tester initials; date; comments (required if test failed) | CTA Test | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | ZM 10/25/2023 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | ZM 10/25/2023 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | ZM 10/25/2023 | Pass | SS 11/12/23: Out of stock message exists | Fail | Avalanche - SA 11/9/23 | Fail | JZ 11/9/2023 - No Message Shown
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | ZM 10/25/2023 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | ZM 10/25/2023 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023 - Add to cart button shown
As a DEVELOPER I want to send a request to retrieve a user’s shopping cart so that I can display what they have saved. | GIVEN a user has items in their shopping cart, WHEN they want to view what items they have saved, THEN they can view their shopping cart. A message of 200 is returned. | Pass | WF 10/25/2023 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN a user doesn't have items in their shopping cart, WHEN a request is sent in, THEN an empty shopping cart is returned with a message of 200. | Pass | WF 10/25/2023 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a Developer I want to create user shopping carts so that they can checkout items. | GIVEN a shopping cart for a user does not exist WHEN I create a shopping cart, THEN I will recieve a 201 created message. | Pass | WF 10/25/2023 | Pass | AR - 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN a shopping cart for a user exists, WHEN I create a shopping cart, THEN I will recieve a 409 conflict message. | Pass | WF 10/25/2023 | Pass | AR - 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a Developer I want to add products to user shopping carts so that they can save items and checkout. | Given that a jersey is in stock, when a user adds an item to their shopping cart, then a request is sent to add it to their shopping cart. A message of 200 is returned | Pass | WF 10/25/2023 | Pass | AR - 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| Given that a jersey is in stock, when a user adds it to their shopping cart, then it should be saved for them to checkout with later. | Pass | WF 10/25/2023 | Pass | AR - 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| Given that a jersey is out of stock, when a user tries to add it to their shopping cart, then they are presented with an error stating the jersey is out of stock. A message of 409 | Pass | WF 10/25/2023 | Pass | AR - 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a DEVELOPER I want to clear the user’s shopping cart when they checkout so that they don’t order the same things last time. | GIVEN a shopping cart with items WHEN the user checks out THEN the shopping cart gets deleted and a message of 200 is returned. | Pass | WF 10/25/2023 | Pass | AR - 11/12/23 | Pass | Avalanche - SA 11/9/23 | Fail | JZ 11/9/2023 - Unable to update cart with empty array
| GIVEN a shopping cart without items WHEN a user tries to checkout and clear their cart THEN they recieve a 200 message. | Pass | WF 10/25/2023 | Pass | AR - 11/12/23 | Pass | Avalanche - SA 11/9/23 | Fail | JZ 11/9/2023 - No backend functionality seen for checkout
As a Customer I want to be able to view a website with a navigation bar and routing so that I can use a dynamic and easy to use website. | **Given** I navigate to the webpage **when** I enter and go from page to page **then** I EXPECT there to be a header/upper bar. | Pass | AR 10/23/23 | Pass | ZM – 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| **Given** I navigate to the webpage **when** go to a different page **then** I EXPECT there to be routing so the site is more "snappy". | Pass | AR 10/23/23 | Pass | ZM – 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| **Given** I navigate to the webpage **when** the page loads **then** I see a homepage with navigation. | Pass | AR 10/23/23 | Pass | ZM – 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a Customer I want to see a list of products so that I choose what to purchase. | GIVEN that the shop sells products WHEN a user views the shop THEN they should see all items that are available to purchase, along with their price and inventory stock | Pass | AR 10/23/23 | Pass | wf 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN that the shop doesnt haven inventory for a product WHEN the user views the shop THEN they don't see the product. | Pass | AR 10/23/23 | Pass | WF 11/13/23 - Note we changed the way they display so this isnt entirely acurate | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a CUSTOMER I want to view the information about a product so that I can see if I want to purchase the product or not. | GIVEN a user is on the website WHEN they click a product THEN they will see all the information about the product. | Pass | AR 10/24/23 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN a user is on the website WHEN they navigate to a product that does not exist THEN they will recieve a 404 message. | Pass | AR 10/24/23 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a Customer I want to search for products so that I find what to purchase. | GIVEN a user has a specific item they are looking for WHEN they search for it THEN it appears in the store inventory. | Pass | ZM 10/25/2023 | Pass | AR - 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN a user searches for a specific item WHEN they search for it THEN they are only able to see the products they search for. | Pass | ZM 10/25/2023 | Pass | AR - 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
AS a Developer I WANT to submit a request to get the products in the inventory whose size, price, and jersey number contains the given property SO THAT I have access to only those products. | **Given** I add more parameters than previously added **when** I do a search for jerseys **then** I expect the jerseys to be returned that fit all the criteria and get a 200 Good returned. | Pass | SS 10/23/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN I submit a request for a product WHEN there the product does not exist THEN the system will return an empty Jersey array | Pass | SS 10/23/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
AS a Developer I WANT to submit a request to get a single product SO THAT I can access the price and quantity. | GIVEN I submit a request for a product WHEN there is a product that matches the request THEN the system will return that product | Pass | ZM 10/25/2023 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN I submit a request for a product WHEN there the product does not exist THEN the system will return an error | Pass | ZM 10/25/2023 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
AS a Developer I WANT to submit a request to get the entire inventory SO THAT I have access to all of the products. | 1. GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) | Pass | SS 10/23/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| 2. GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | Pass | SS 10/23/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a Developer I want to submit a request to delete a single product SO THAT it is no longer in the inventory. | GIVEN I submit a request to delete a jersey WHEN the jersey does not exist THEN the system will return a 404 (Not Found). | Pass | SS 10/23/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN I submit a request to delete a product WHEN a product with the given name exists THEN the system should delete the product, remove it from the inventory, save to the persistent store, and return a status code of 200 (OK). | Pass | SS 10/23/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
AS a Developer I WANT to submit a request to create a new product (name, price, quantity) SO THAT it is available to in the inventory. | GIVEN I submit a product object WHEN no product with the given name exists THEN the system should create the product, add it to the inventory, save to the persistent store, and return the product object and a status code of 201 (CREATED) | Pass | ZM 10/25/2023 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN I submit a product object WHEN a product with the given name already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | ZM 10/25/2023 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Fail | JZ 11/9/2023 - No conflicts, just creates jersey with dif ID
AS a Developer I WANT to submit a request to update a jersey SO THAT I can keep the jerseys up to date. | 1. GIVEN I submit a request to update the product WHEN that product exists in the inventory THEN the system should update the product and return a status code of 200 (OK) | Pass | SS 10/23/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| 2. GIVEN I submit a request to update the product WHEN no product exists that matches THEN the system should return a status code of 404 (NOT FOUND) | Pass | SS 10/23/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
AS a Developer I WANT to submit a request to get the products in the inventory whose name contains the given text SO THAT I have access to only those products. | GIVEN I submit a search request for a word WHEN the word has matches in the criteria THEN the system will return a list of jerseys that match the search and return a 200 (OK). | Pass | AR 10/24/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN I submit a search request for a word WHEN the word has zero matches in the criteria THEN the system will return an empty list of jerseys and return a 200 (OK). | Pass | AR 10/24/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a Customer I want to log-in to the system so that I can look at the store. | GIVEN a user wants to log in to the system, WHEN they enter their username, THEN they are logged in and can see the store. | Pass | AR 11/8/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN A user registers in the system WHEN the user does not already exists THEN a new shopping cart is created for them | Pass | AR 11/8/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN a user logs in as 'admin', WHEN they enter the site, THEN they can see admin functionality. | Pass | AR 11/8/23 | Pass | WF 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As an Admin I want to use a dashboard to manage the inventory so that I can easily change the inventory. | GIVEN I want to add/remove/update products WHEN I click on the dashboard THEN I should see options to add/remove/update products |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | ZM – 11/13/23 | Fail | Avalanche - SA 11/9/23; only missing update | Pass | JZ 11/9/2023
| GIVEN I open the dashboard WHEN I add/remove/update products from the dashboard THEN those changes should be seen by customers. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | ZM – 11/13/23 | Fail | Avalanche - SA 11/9/23; only missing update | Pass | JZ 11/9/2023
As an admin I want to delete an item from the store so that people can’t purchase it. | GIVEN a jersey exists on the store page, WHEN I click delete, THEN it gets removed from the store. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | ZM – 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| GIVEN a jersey doesn't exist, WHEN an admin tries to delete it, THEN an error is thrown. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | ZM – 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a user I want to review the product I ordered so that other people know if I was satisfied. | Given a user is on a product page, when they complete a review, it creates a review and displays it on the page. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| Given a user is logged in when they look at reviews, they can leave a review. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| Given a user is not logged in when they look at reviews, then they cannot leave a review |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a user I want to view the reviews of a product so that I know if I want to purchase it. | Given a user is on the site, when they view a product page, then they should see all the product reviews for that item. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| Given there are no reviews for a product, when a user views a product page, then they should see a message stating no reviews are available. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | SS 11/12/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As an admin, I want to delete a review, so that they can be moderated. | Given an admin is logged in, when they view the product page, then they can delete reviews. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | ZM – 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As an admin I want to delete an item from the store so that people can’t purchase it. | Given a jersey exists on the store page, when I click delete, then it gets removed from the store. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | ZM – 11/13/23 | Pass | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
| Given a jersey doesn't exist, if an admin tries to delete it, an error is thrown. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | ZM – 11/13/23 | Fail | Avalanche - SA 11/9/23 | Pass | JZ 11/9/2023
As a admin I want to update the information on a jersey through the website so that I can seamlessly change the information to stay up to date. | GIVEN I want to update information about a jersey WHEN I update one of the attributes THEN the change should be reflected everywhere on the store. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | WF 11/13/23 | Fail | Avalanche - SA 11/9/23; missing update | Pass | JZ 11/9/2023
Updated Search Fields (2) | **Given** the website/search is viewed **when** I enter the website **then** the new search fields should be displayed. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | SS 11/12/23
| **Given** I enter the new search parameters **when** there are jerseys that fit the parameters **then** the jerseys should be displayed. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | SS 11/12/23
| **Given** I enter information into the new parameters **when** there are no jerseys that fit the parameters **then** no jerseys should be displayed. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | SS 11/12/23
User Viewing Shopping Cart (3) | Given a user navigates to their shopping cart, then the items they have added appear. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | AR - 11/12/23
| Given a user logs out of their account, when they return, then the items in their cart appear. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | AR - 11/12/23
User Adding to Shopping Cart (3) | Given a user views the product page, WHEN they add a jersey to their shopping cart, THEN their shopping cart gets updated. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | AR - 11/12/23
| Given a user views a jersey, WHEN they add a jersey they already have to their shopping cart, THEN their shopping cart gets updated with the new quantity. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | AR - 11/12/23
| Given a user has the jersey in their shopping cart, WHEN they add the jersey to their cart, then the quantity increases. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | AR - 11/12/23
User Removing from Shopping Cart (3) | Given a user has a jersey in their shopping cart, when they remove the item from their shopping cart, then the item is removed. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | AR - 11/12/23
User Updating Shopping Cart (3) | Given a user has a jersey in their shopping cart, when they update the quantity of that jersey then the shopping cart is updated. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | AR - 11/12/23
Payment information (3) | Given a user has a shopping cart with items, when they click the checkout button, then they are prompted to input payment information. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | SS 11/12/23 Note: You cannot click checkout UNTIL payment info is inputed
Display order receipt (3) | **Given** I checkout my cart **when** I finish checking out **then** I expect an itemized receipt to be displayed. |  | NOT IMPLEMENTED IN SPRINT 2 | Pass | AR - 11/12/23